## GanttChart
Project Name
Company Name
| Project Lead: | John Doe
| Today's Date: | 2020-03-05 |  | (vertical red line)
| Start Date: | 2020-01-03 | 2020-01-03 | [6 empty] | 0 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-11 | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2019-12-30: 2019-12-30; 2020-01-06: 2020-01-06; 2020-01-13: 2020-01-13; 2020-01-20: 2020-01-20; 2020-01-27: 2020-01-27; 2020-02-03: 2020-02-03; 2020-02-10: 2020-02-10; 2020-02-17: 2020-02-17; 2020-02-24: 2020-02-24; 2020-03-02: 2020-03-02; 2020-03-09: 2020-03-09; 2020-03-16: 2020-03-16; 2020-03-23: 2020-03-23; 2020-03-30: 2020-03-30; 2020-04-06: 2020-04-06; 2020-04-13: 2020-04-13; 2020-04-20: 2020-04-20; 2020-04-27: 2020-04-27; 2020-05-04: 2020-05-04; 2020-05-11: 2020-05-11; 2020-05-18: 2020-05-18; 2020-05-25: 2020-05-25; 2020-06-01: 2020-06-01; 2020-06-08: 2020-06-08; 2020-06-15: 2020-06-15; 2020-06-22: 2020-06-22; 2020-06-29: 2020-06-29; 2020-07-06: 2020-07-06; 2020-07-13: 2020-07-13; 2020-07-20: 2020-07-20; 2020-07-27: 2020-07-27; 2020-08-03: 2020-08-03; 2020-08-10: 2020-08-10; 2020-08-17: 2020-08-17; 2020-08-24: 2020-08-24; 2020-08-31: 2020-08-31; 2020-09-07: 2020-09-07; 2020-09-14: 2020-09-14; 2020-09-21: 2020-09-21; 2020-09-28: 2020-09-28; 2020-10-05: 2020-10-05; 2020-10-12: 2020-10-12; 2020-10-19: 2020-10-19; 2020-10-26: 2020-10-26; 2020-11-02: 2020-11-02; 2020-11-09: 2020-11-09; 2020-11-16: 2020-11-16; 2020-11-23: 2020-11-23
1 | Task Category 1 | John | 2020-01-03 | 2020-03-16 | 74 | 79.86% | 52 | 59 | 15
1.1 | Sub Task |  | 2020-01-03 | 2020-01-20 | 18 | 100% | 12 | 18 | 0
1.2 | Sub Task |  | 2020-01-21 | 2020-02-19 | 30 | 95% | 22 | 28 | 2
1.3 | Sub Task |  | 2020-01-22 | 2020-02-09 | 19 | 95% | 13 | 18 | 1
1.4 | Sub Task |  | 2020-02-10 | 2020-03-17 | 37 | 50% | 27 | 18 | 19
2 | Task Category 2 | Jane | 2020-03-01 | 2020-05-11 | 72 | 13.47% | 51 | 9 | 63
2.1 | Sub Task |  | 2020-03-01 | 2020-03-17 | 17 | 50% | 12 | 8 | 9
2.2 | Sub Task |  | 2020-03-01 | 2020-03-17 | 17 | 30% | 12 | 5 | 12
2.3 | Sub Task |  | 2020-03-18 | 2020-04-25 | 39 | 0% | 28 | 0 | 39
2.4 | Sub Task |  | 2020-04-15 | 2020-05-12 | 28 | 0% | 20 | 0 | 28
3 | Task Category 3 | Bill | 2020-04-25 | 2020-08-01 | 99 | 0% | 70 | 0 | 99
3.1 | Sub Task |  | 2020-04-25 | 2020-05-11 | 17 | 0% | 11 | 0 | 17
3.2 | Sub Task |  | 2020-05-12 | 2020-05-28 | 17 | 0% | 13 | 0 | 17
3.3 | Sub Task |  | 2020-05-29 | 2020-07-04 | 37 | 0% | 26 | 0 | 37
3.4 | Sub Task |  | 2020-07-05 | 2020-08-02 | 29 | 0% | 20 | 0 | 29
Note on A10: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on H10: Working Days Counts only Mon-Fri, using the NETWORKDAYS() formula. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached. Note: If the start date is later changed, the number of working days may also change.
Note on I10: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J10: Calendar Days Remaining This column is calculated by subtracted the Days Complete from the Duration.
Note on F10: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F13=MAX(E14:E17)-D13
Note on G10: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G13=SUMPRODUCT(F14:F17,G14:G17)/SUM(F14:F17) Note: If you insert rows, make sure that the calculation is updated correctly.
Note on E10: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on D10: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Sample Note
Sample Note
Sample Note